## WB! Status
What'sBest! 7.0 Status Report
2004-04-15 15:04
Solver memory allocated: 131072
Model Type: LINEAR
The smallest and largest coefficients in the model were:
1.0000000 4550000.0
The smallest coefficient occurred in constraint cell: Sheet1!I6
on optimizable cell: <RHS>
The largest coefficient occurred in constraint cell: Sheet1!G22
on optimizable cell: <RHS>
CLASSIFICATION STATISTICS Current / Maximum
---------------------------------------------------
Numeric 172 / 1000000
Adjustable 30
Constraints 34
Integers 0
Optimizable 81
Nonlinear 0
Coefficients 149
Tries: 20 Infeasibility: 0 Objective: 4690000
Solution Status: GLOBALLY OPTIMAL.
Solution Time: 0 Hours 0 Minutes 1 Seconds
End of report.

## Sheet1
Reliable Construction Co. Project Scheduling Problem with Time-Cost Trade-offs
What'sBest Model of Optimal Crashing
[6 empty] | Crash cost | Maximum |  | Actual
|  | Time |  | Cost |  | per Week | Time |  | Time Re- | Start | Finish | Precedence
| Activity | Normal | Crash | Normal | Crash | saved | Reduction |  | duction | Time | Time | Constraints |  | Predecessors
| A | 2 | 1 | 180000 | 280000 | 100000 | 1 | #VALUE! | 0 | 0 | 2
| B | 4 | 2 | 320000 | 420000 | 50000 | 2 | #VALUE! | 0 | 2 | 6 | #VALUE! |  | A
| C | 10 | 7 | 620000 | 860000 | 80000 | 3 | #VALUE! | 0 | 6 | 16 | #VALUE! |  | B
| D | 6 | 4 | 260000 | 340000 | 40000 | 2 | #VALUE! | 0 | 16 | 22 | #VALUE! |  | C
| E | 4 | 3 | 410000 | 570000 | 160000 | 1 | #VALUE! | 0 | 16 | 20 | #VALUE! |  | C
| F | 5 | 3 | 180000 | 260000 | 40000 | 2 | #VALUE! | 2 | 20 | 23 | #VALUE! |  | E
| G | 7 | 4 | 900000 | 1020000 | 40000 | 3 | #VALUE! | 0 | 22 | 29 | #VALUE! |  | D
| H | 9 | 6 | 200000 | 380000 | 60000 | 3 | #VALUE! | 0 | 29 | 38 | #VALUE! | #VALUE! | E | G
| I | 7 | 5 | 210000 | 270000 | 30000 | 2 | #VALUE! | 0 | 16 | 23 | #VALUE! |  | C
| J | 8 | 6 | 430000 | 490000 | 30000 | 2 | #VALUE! | 2 | 23 | 29 | #VALUE! | #VALUE! | F | I
| K | 4 | 3 | 160000 | 200000 | 40000 | 1 | #VALUE! | 0 | 29 | 33 | #VALUE! |  | J
| L | 5 | 3 | 250000 | 350000 | 50000 | 2 | #VALUE! | 0 | 29 | 34 | #VALUE! |  | J
| M | 2 | 1 | 100000 | 200000 | 100000 | 1 | #VALUE! | 0 | 38 | 40 | #VALUE! |  | H
| N | 6 | 3 | 330000 | 510000 | 60000 | 3 | #VALUE! | 0 | 34 | 40 | #VALUE! | #VALUE! | K | L
| FINISH | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 40 | 40 | #VALUE! | #VALUE! | M | N
[5 empty] | Total cost: | 4690000 | Max Time: |  | 40 | #VALUE! | 40 | Actual Finish
Color codes
Data
Decision
Formula
Constraint
Objective
This sheet is set up to be compatible
with the What'sBest solver.
To download it see:
http://www.lindo.com
Making modifications:
To add a new activity:
1) Insert ¦ Row in the interior of each of the 2 Activity sections.
2) Copy an existing row into the new one
to copy the formulae and constraints.
3) Enter data specific to the new row in 1st section.
To add a new Precedence:
1) Insert ¦ Column in the interior of the Precedence section.
2) Copy an existing column into the new one
to copy the formulae and constraints