## WB! Status
What'sBest! 7.0 Status Report
2004-04-15 13:44
Solver memory allocated: 131072
Model Type: LINEAR
The smallest and largest coefficients in the model were:
1.0000000 160.00000
The smallest coefficient occurred in constraint cell: Sheet1!J5
on optimizable cell: Sheet1!J6
The largest coefficient occurred in constraint cell: Sheet1!I6
on optimizable cell: Sheet1!F11
CLASSIFICATION STATISTICS Current / Maximum
---------------------------------------------------
Numeric 735 / 1000000
Adjustable 30
Constraints 34
Integers 0
Optimizable 98
Nonlinear 0
Coefficients 183
Tries: 27 Infeasibility: 0 Objective: 140
Solution Status: GLOBALLY OPTIMAL.
Solution Time: 0 Hours 0 Minutes 1 Seconds
End of report.

## Sheet1
Reliable Construction Co. Project Scheduling Problem with Time-Cost Trade-offs | [15 empty] | Precedence Section
What'sBest Model of Optimal Crashing
[10 empty] | Predecessor: | A | B | C | C | E | D | E | G | C | F | I | J | J | H | K | L | M | N
| Activity Section | [8 empty] | Successor: | B | C | D | E | F | G | H | H | I | J | J | K | L | M | N | N | FINISH | FINISH
| Time |  | Cost |  | Max |  | Actual |  |  | Cost | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Activity | Normal | Crash | Normal | Crash | Crash |  | Crash | Start | End | 1220000 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
A | 2 | 1 | 180000 | 280000 | 1 | #VALUE! | 0 | 0 | 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 4 | 2 | 320000 | 420000 | 2 | #VALUE! | 0 | 2 | 6 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | 10 | 7 | 620000 | 860000 | 3 | #VALUE! | 0 | 6 | 16 |  | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 6 | 4 | 260000 | 340000 | 2 | #VALUE! | 0 | 16 | 22 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 4 | 3 | 410000 | 570000 | 1 | #VALUE! | 0 | 16 | 20 |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 5 | 3 | 180000 | 260000 | 2 | #VALUE! | 2 | 20 | 23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G | 7 | 4 | 900000 | 1020000 | 3 | #VALUE! | 0 | 22 | 29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
H | 9 | 6 | 200000 | 380000 | 3 | #VALUE! | 0 | 29 | 38 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
I | 7 | 5 | 210000 | 270000 | 2 | #VALUE! | 0 | 16 | 23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
J | 8 | 6 | 430000 | 490000 | 2 | #VALUE! | 2 | 23 | 29 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
K | 4 | 3 | 160000 | 200000 | 1 | #VALUE! | 0 | 30 | 34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
L | 5 | 3 | 250000 | 350000 | 2 | #VALUE! | 0 | 29 | 34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
M | 2 | 1 | 100000 | 200000 | 1 | #VALUE! | 0 | 38 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
N | 6 | 3 | 330000 | 510000 | 3 | #VALUE! | 0 | 34 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
FINISH | 0 | 0 | 0 | 0 | 0 | #VALUE! | 0 | 40 | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#VALUE!
[8 empty] | Duedate= | 40 | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | B | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | C | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | D | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | E | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | F | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | G | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | H | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | J | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
[10 empty] | N | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
[10 empty] | FINISH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Color codes
Data
Decision
Formula
Constraint
Objective
This sheet is set up to be compatible
with the What'sBest solver.
To download it see:
http://www.lindo.com
Making modifications:
To add a new activity:
1) Insert ¦ Row in the interior of each of the 2 Activity sections.
2) Copy an existing row into the new one
to copy the formulae and constraints.
3) Enter data specific to the new row in 1st section.
To add a new Precedence:
1) Insert ¦ Column in the interior of the Precedence section.
2) Copy an existing column into the new one
to copy the formulae and constraints