## Login
LOGIN Information
USERNAME: | USER
PASSWORD: | USER
PROJECT: | APEX

## Res_Control_Act
|  |  | PRIMAVERA PROJECT PLANNER |  |  |  | Start Date 1/5/94
|  |  | Resource Control - Activity Report |  |  |  | Fin Date 1/13/94 4:00:00 PM
|  |  | Project OUTG |  |  |  | Data Date 1/8/94
|  | Cost |  | Actual | Actual | Estimate To
Activity | Resource | Account | Budget | To Date | This Period | Complete | Forecast | Varaince
AUA407 | 3 - Repair Condenser Boxes and Repack Valves
| BOILERMK | 422 L | 32 | 0 | 0 | 32 | 32 | 0
| TOTAL : |  | 32 | 0 | 0 | 32 | 32 | 0
AUA410 | 4 - ST/Topic - Repair Inner Condenser Drain
| BOILERMK | 422 L | 64 | 0 | 0 | 0 | 0 | 64
| TOTAL : |  | 64 | 0 | 0 | 0 | 0 | 64
| REPORT TOTALS : |  | 96 | 0 | 0 | 32 | 32 | 64

## Cost_Control_Act
|  |  | PRIMAVERA PROJECT PLANNER |  |  |  | Start Date 1/5/94
|  |  | Cost Control - Activity Report |  |  |  | Fin Date 1/13/94 4:00:00 PM
|  |  | Project OUTG |  |  |  | Data Date 1/8/94
|  | Cost |  | Actual | Actual | Estimate To
Activity | Resource | Account | Budget | To Date | This Period | Complete | Forecast | Varaince
AUA407 | 3 - Repair Condenser Boxes and Repack Valves
| BOILERMK | 422 L | 672 | 0 | 0 | 672 | 672 | 0
| TOTAL : |  | 672 | 0 | 0 | 672 | 672 | 0
AUA410 | 4 - ST/Topic - Repair Inner Condenser Drain
| BOILERMK | 422 L | 1344 | 0 | 0 | 0 | 0 | 1344
| TOTAL : |  | 1344 | 0 | 0 | 0 | 0 | 1344
| REPORT TOTALS : |  | 2016 | 0 | 0 | 672 | 672 | 1344
BA831 | OPENG | 13426 L | 4800 | 0 | 0 | 0 | 4800 | 4800 | 0
BA831 | PF | 13426 L | 2560 | 0 | 0 | 0 | 2560 | 2560 | 0
| TOTAL : |  | 0 | 0 | 7360 | 7360 | 0 | 0 | 0
BA840 | PLUMBER | 13436 L | 15840 | 0 | 0 | 0 | 15840 | 15840 | 0
BA840 | PIPING | 13436 M | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL : |  | 0 | 0 | 15840 | 15840 | 0 | 0 | 0
BA850 | ELECTRCN | 13436 L | 19200 | 0 | 0 | 0 | 19200 | 19200 | 0
| TOTAL : |  | 0 | 0 | 19200 | 19200 | 0 | 0 | 0
BA860 | ELEV | 13416 C | 28800 | 0 | 0 | 0 | 28800 | 28800 | 0
| TOTAL : |  | 0 | 0 | 28800 | 28800 | 0 | 0 | 0
BA870 | PF | 13436 L | 3072 | 0 | 0 | 0 | 3072 | 3072 | 0
| TOTAL : |  | 0 | 0 | 3072 | 3072 | 0 | 0 | 0
BA871 | OPENG | 13426 L | 960 | 0 | 0 | 0 | 960 | 960 | 0
| TOTAL : |  | 0 | 0 | 960 | 960 | 0 | 0 | 0
BA880 | UNASSIGN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL : |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA890 | FNSHCARP | 13636 L | 30720 | 0 | 0 | 0 | 30720 | 30720 | 0
| TOTAL : |  | 0 | 0 | 30720 | 30720 | 0 | 0 | 0
BA899 | UNASSIGN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL : |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA900 | FNSHCARP | 13636 L | 30720 | 0 | 0 | 0 | 30720 | 30720 | 0
| TOTAL : |  | 0 | 0 | 30720 | 30720 | 0 | 0 | 0
BA901 | ELECTRCN | 13626 L | 3072 | 0 | 0 | 0 | 3072 | 3072 | 0
| TOTAL : |  | 0 | 0 | 3072 | 3072 | 0 | 0 | 0
BA902 | SM | 13436 L | 5440 | 0 | 0 | 0 | 5440 | 5440 | 0
| TOTAL : |  | 0 | 0 | 5440 | 5440 | 0 | 0 | 0
BA910 | FLRLYR | 13616 L | 3520 | 0 | 0 | 0 | 3520 | 3520 | 0
| TOTAL : |  | 0 | 0 | 3520 | 3520 | 0 | 0 | 0
BA911 | FNSHCARP | 13636 L | 7680 | 0 | 0 | 0 | 7680 | 7680 | 0
| TOTAL : |  | 0 | 0 | 7680 | 7680 | 0 | 0 | 0
BA912 | PLUMBER | 13626 L | 2640 | 0 | 0 | 0 | 2640 | 2640 | 0
| TOTAL : |  | 0 | 0 | 2640 | 2640 | 0 | 0 | 0
BA913 | ELEV | 13416 L | 3840 | 0 | 0 | 0 | 3840 | 3840 | 0
| TOTAL : |  | 0 | 0 | 3840 | 3840 | 0 | 0 | 0
BA930 | PAINTER | 13646 L | 16560 | 0 | 0 | 0 | 16560 | 16560 | 0
BA930 | PAINT | 13646 M | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL : |  | 0 | 0 | 16560 | 16560 | 0 | 0 | 0
BA940 | FNSHCARP | 13636 L | 1024 | 0 | 0 | 0 | 1024 | 1024 | 0
BA940 | PAINTER | 13646 | 736 | 0 | 0 | 0 | 736 | 736 | 0
BA940 | LABORER | 13636 L | 800 | 0 | 0 | 0 | 800 | 800 | 0
| TOTAL : |  | 0 | 0 | 2560 | 2560 | 0 | 0 | 0
BA941 | OPENG | 13426 L | 960 | 0 | 0 | 0 | 960 | 960 | 0
| TOTAL : |  | 0 | 0 | 960 | 960 | 0 | 0 | 0
BA950 | UNASSIGN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL : |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA960 | FNSHCARP | 13636 L | 2048 | 0 | 0 | 0 | 2048 | 2048 | 0
BA960 | PAINTER | 13646 L | 1472 | 0 | 0 | 0 | 1472 | 1472 | 0
BA960 | LABORER | 13636 L | 1280 | 0 | 0 | 0 | 1280 | 1280 | 0
| TOTAL : |  | 0 | 0 | 4800 | 4800 | 0 | 0 | 0
BA970 | UNASSIGN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL : |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CS300 | ATM ENG | 12101 L | 5280 | 0 | 0 | 0 | 5280 | 5280 | 0
| TOTAL : |  | 0 | 0 | 5280 | 5280 | 0 | 0 | 0
CS305 | ATM ENG | 12223 L | 528 | 0 | 0 | 0 | 528 | 528 | 0
CS305 | FLD ENG1 | 12223 L | 4000 | 0 | 0 | 0 | 4000 | 4000 | 0
| TOTAL : |  | 0 | 0 | 4528 | 4528 | 0 | 0 | 0
CS310 | PRG MGR | 12101 L | 2019 | 0 | 0 | 0 | 2019 | 2019 | 0
| TOTAL : |  | 0 | 0 | 2019 | 2019 | 0 | 0 | 0
CS311 | UNASSIGN |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL : |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CS315 | FLD ENG3 | 12213 L | 1020 | 0 | 0 | 0 | 1020 | 1020 | 0
| TOTAL : |  | 0 | 0 | 1020 | 1020 | 0 | 0 | 0
CS400 | ATM ENG | 12312 L | 440 | 0 | 0 | 0 | 440 | 440 | 0
| TOTAL : |  | 0 | 0 | 440 | 440 | 0 | 0 | 0
CS410 | PRG MGR | 12312 L | 134.6 | 0 | 0 | 0 | 134.6 | 134.6 | 0
| TOTAL : |  | 0 | 0 | 134.6 | 134.6 | 0 | 0 | 0
CS420 | ACCTS | 12312 L | 32 | 0 | 0 | 0 | 32 | 32 | 0
| TOTAL : |  | 0 | 0 | 32 | 32 | 0 | 0 | 0
CS430 | DES ENG | 12311 L | 4800 | 0 | 0 | 0 | 4800 | 4800 | 0
| TOTAL : |  | 0 | 0 | 4800 | 4800 | 0 | 0 | 0
CS440 | ATM ENG | 12311 L | 440 | 0 | 0 | 0 | 440 | 440 | 0
CS440 | PRG MGR | 12311 L | 673 | 0 | 0 | 0 | 673 | 673 | 0
| TOTAL : |  | 0 | 0 | 1113 | 1113 | 0 | 0 | 0
CS450 | VENDOR | 12312 M | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL : |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CS700 | FLD ENG1 | 12213 L | 2800 | 0 | 0 | 0 | 2800 | 2800 | 0
| TOTAL : |  | 0 | 0 | 2800 | 2800 | 0 | 0 | 0
CS710 | FLD ENG1 | 12213 L | 10000 | 0 | 0 | 0 | 10000 | 10000 | 0
| TOTAL : |  | 0 | 0 | 10000 | 10000 | 0 | 0 | 0
CS720 | FLD ENG1 | 12213 L | 2000 | 0 | 0 | 0 | 2000 | 2000 | 0
| TOTAL : |  | 0 | 0 | 2000 | 2000 | 0 | 0 | 0
CS730 | FLD ENG1 | 12213 L | 6000 | 0 | 0 | 0 | 6000 | 6000 | 0
| TOTAL : |  | 0 | 0 | 6000 | 6000 | 0 | 0 | 0
CS740 | FLD ENG2 | 12213 L | 8000 | 0 | 0 | 0 | 8000 | 8000 | 0
CS740 | FLD ENG3 | 12213 L | 6800 | 0 | 0 | 0 | 6800 | 6800 | 0
| TOTAL : |  | 0 | 0 | 14800 | 14800 | 0 | 0 | 0